## Slide 1
Vincent // 2001591880
Muhammad Setiawan // 2001611762
Andrew Jonatan // 2001580252
Cornelia Dyana Rastiti // 2001597770

## Slide 2: Roles
Vincent : programmer, primary proj. manager
Wawan : level designer
Yana : artist, secondary proj. manager
Andrew : audio (music and sfx)

## Slide 3: Game Overview
Mobile, casual, landscape, 2D platformer
Game engine : Unity
10 – 15 levels
Same level layouts (per 5 levels), different challenges
  Mainly getting from point A (spawn point) to point B (check-point)

## Slide 4: Group Workflow Timeline
W1 (19 – February 25th) : Game design, idea exploration
W2 (February 26th – March 4th) : Finishing up on game design
W3 (5 – March 11th) : Respective works
W4 (12 – March 18th) : Respective works
W5 (19 – March 25th) : prototype is finished, at least half of the levels are done
W6 (26 – April 1st) : Respective works
W7 (2 – April 8th) : Respective works
W8 (9 – April 15th) : Respective works
W9 (16 – April 22nd) : game is finished and polished (overall group deadline : April 20th)

## Slide 5: Individual Workflow Timeline
Vincent
W1 + W2 : game design (prog. language, layout, etc.)
W3 : basic programming
W4 + W5 : first five levels are done, also main menu (playable build)
W6 + W7 : second set of five levels finished
W8 + W9 : third set of five levels are finished and final build is bug-free
Wawan
W1 + W2 : overall game design
W3 + W4 + W5 : polish level design
W6 : balancing, additional changes / fixes
W7 + W8 + W9 : polish level design and monitor progress, constant playtesting

## Slide 6
Yana
W1 + W2 : overall game design (colors used, art style, characters, objects, etc.), basic sketches
W3 : game objects and background(s)
W4 : UI buttons, basic character animation sketches (keyframes)
W5 + W6 + W7 : character animations
W8 + W9 : polishing (effects, etc.)
Andrew
W1 + W2 : overall game design (type of music, instruments, sfx), music samples
W3 + W4 + W5 : majority of the music are done, important sfx are done
W6 + W7 + W8 + W9 : music are more polished (with extras), extra / additional sfx added

## Slide 7: Progress
Decided UI layout
Decided main / playable character
Decided objective
Decided song theme / mood
Decided color palettes
Decided backgrounds

## Slide 8: Sketches / General Design

## Slide 9: Thank you